## UCO_TestCases
TC_ID | Module2 | TC Description | Pre-Conditions | Test Steps | Expected Results | Status | Remarks | Dev. Updated Remarks
UCOTC_029 | Access Restrictions | Verify that the revoke button appears only when the NFA is present in the next user’s queue. | NFA in next user’s queue. | 1. Check visibility of Revoke button. | Button appears only when NFA is in next user’s queue. | Pass
UCOTC_034 | Access Restrictions | Verify that confidential cases do not appear in the “All” list for users who are not involved. | Confidential case exists. | 1. Check "All" list for all users. | Confidential cases not visible to uninvolved users. | Fail | Under Development
UCOTC_057 | Access Restrictions | Verify that the system warns the Initiator before discarding an NFA to prevent accidental deletion. | The Initiator has an unsaved or draft NFA | Log in as the Initiator. Navigate to the draft section. Click "Discard" | A warning prompt appears, preventing accidental deletion | Pass
UCOTC_067 | Access Restrictions | Verify that when the user checks "Top Sheet," the additional field becomes mandatory for the Initiator to fill. | Initiator selects "Top Sheet" checkbox | Log in as the Initiator. Start an NFA and check "Top Sheet." Try submitting without entering additional details | System prevents submission and displays an error prompting additional input | Pass
UCOTC_074 | Access Restrictions | Verify that the recommender cannot see NFAs of other departments unless part of a cross-department approval. | Multiple department NFAs exist; recommender is not in matrix of others. | Log in as recommender. Search for NFAs from other departments. | Other department NFAs are not accessible unless cross-department flag is active. | Pass
UCOTC_075 | Access Restrictions | Verify that the recommender can view the NFA in read-only mode, including all fields and attachments. | NFA is in recommender's queue. | Open the NFA. Try editing fields or attachments. | All data is non-editable and attachments are view-only. | Fail
UCOTC_078 | Access Restrictions | Verify that the recommender cannot approve an NFA if their signature is not uploaded. | Recommender has no uploaded signature. | Open an NFA. Try to approve it. | System shows error requiring signature upload. | Fail
UCOTC_079 | Access Restrictions | Verify that the recommender receives an error if trying to refer an NFA to a user not onboarded in the system. | User to be referred is not onboarded | Enter unregistered user in refer field. Click "Refer". | System throws error – “User not found or not onboarded.” | Pass
UCOTC_089 | Access Restrictions | Verify that the recommender can view previous annotations and versions of uploaded documents. | NFA has multiple versions. | Open document viewer. Navigate to version history. | All versions with user info and actions are listed. | Fail
UCOTC_093 | Access Restrictions | Verify that the recommender cannot act on an NFA that has already been approved. | NFA status is "Approved" | Open an already-approved NFA. Attempt to click Approve/Refer/Raise Query. | All action buttons are disabled or hidden. | Fail
UCOTC_094 | Access Restrictions | Verify that tooltips or help texts are shown when the recommender hovers over action buttons. | NFA is open in recommender view | Hover over action buttons (Approve, Refer, etc.). | Tooltip appears | Pass
UCOTC_097 | Access Restrictions | Verify that the recommender cannot upload or delete documents; only view them in read-only mode. | NFA contains uploaded documents. | Open document section. Try to upload or delete. | No upload/delete options visible. Documents are view-only. | Fail
UCOTC_100 | Access Restrictions | Verify revoke conditions (Referred, Forwarded) | Case in correct state. | Attempt revoke in each case | Revoke allowed only if target hasn't acted. Blocked if already processed | Pass
UCOTC_107 | Access Restrictions | Verify Access Restrictions | Logged in as recommender. | Try create/discard/edit NFA, logout mid-case, view docs after leaving form. | Access denied for all restricted actions. | Fail
UCOTC_115 | Access Restrictions | Verify Case Visibility Post Approval | NFA forwarded/referred then approved. | Login as referred user. | Case disappears post-approval from their dashboard. | Pass
UCOTC_116 | Access Restrictions | Verify Decision Options Availability | NFA is pending with recommender. | Open NFA and check visible action buttons. | Buttons shown - Approve, Raise Query, Reject, Refer, Forward, Revoke. | Pass
UCOTC_118 | Access Restrictions | Verify Raise Query (General + First Recommender) | NFA under recommender review. | Raise query with/without comment. | Query sent to N-1 or Initiator. Comment mandatory. Audit trail updated. | Fail | Case should be to one step back ecommender but case is nowhere
UCOTC_124 | Access Restrictions | Verify Forwarded user opens NFA in read-only mode with access to all comments and documents. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_125 | Access Restrictions | Verify Forwarded user can approve the NFA if it has no issues. | NFA is forwarded by the recommender. | Login as Recommender or Approver Click Forward and select a valid user Login as the Forwarded User Open the forwarded NFA Add remarks and click Approve | NFA should be approved successfully by the forwarded user Status updates in audit trail System routes case to next approver (if any) | Pass
UCOTC_130 | Access Restrictions | Verify Forwarded NFA disappears after user takes action. | NFA is forwarded by the recommender. | Login as the Forwarded User Open the NFA Approve or Reject it Refresh or revisit the dashboard | NFA should disappear from forwarded user’s dashboard after action NFA should move to next level (or end) Visible in audit trail only | Pass
UCOTC_138 | Access Restrictions | Verify Only one action (approve or reject) should be allowed at a time. | NFA is forwarded by the recommender. | Login as Recommender/Approver or Forwarded user Open NFA Check UI for actions available (Approve / Reject / Query) | System should not allow selecting multiple actions together UI should disable one when the other is selected Only one valid action can be submitted | Pass
UCOTC_141 | Access Restrictions | Verify Attempt to access non-assigned NFA via direct URL should result in access denied. | NFA is forwarded by the recommender. | Login as User A (not involved in the NFA) Try to access the NFA using direct URL (copied from User B) Observe system response | System should show “Access Denied” or “You are not authorized to view this NFA.” User should be redirected to dashboard | Pass
UCOTC_149 | Access Restrictions | Verify Confirm forwarded user’s comments are visible to all future reviewers. | NFA is forwarded by the recommender. | Forward an NFA to User X User X adds remarks and approves Login as next-level approver Open the same NFA and check remarks section | Remarks entered by forwarded user should be visible in the comment trail Clearly show: “Action taken by [User X] - Forwarded User” | Pass
UCOTC_150 | Access Restrictions | Verify Forwarded user cannot forward or assign to others. | NFA is forwarded by the recommender. | Login as a Forwarded User Open the NFA Try to locate “Forward” or “Refer” button | Forward, Refer, and Revoke buttons should be disabled or hidden Only Approve / Reject should be allowed | Pass
UCOTC_151 | Access Restrictions | Verify Forwarded user can view the document annotations clearly without editing. | NFA with annotations is forwarded. | - Login as forwarded user. - Open the document. | Annotations are visible and not editable. | Pass
UCOTC_152 | Access Restrictions | Verify Forwarded user sees correct NFA metadata including ID, Title, and Department. | Valid forwarded NFA exists. | - Login and open the NFA. | NFA metadata matches expected values. | Pass
UCOTC_153 | Access Restrictions | Verify Forwarded user receives validation error when attempting to act without signature. | Signature is not uploaded for the user. | - Open NFA. - Click approve without signature. | Error prompts signature upload. | Fail | User can Proceed without signature as per Dev.
UCOTC_157 | Access Restrictions | Verify Forwarded user cannot take action if case is discarded by initiator. | NFA is discarded post forwarding. | - Try to act on the NFA. | System blocks the action. | Fail | Forward Functionality is not working
UCOTC_158 | Access Restrictions | VerifyForwarded user sees 'case revoked' tag if recommender revoked NFA before action. | Recommender revoked case. | - Login and view dashboard. | Revoked tag is shown. No actions allowed. | Fail | Forward Functionality is not working
UCOTC_159 | Access Restrictions | Verify Forwarded user can only act once; second attempt should fail. | NFA is acted upon once. | - Take action twice on same NFA. | Second attempt is blocked with message. | Pass
UCOTC_163 | Access Restrictions | Verify Forwarded user cannot perform bulk actions on multiple NFAs. | Multiple NFAs forwarded. | - Try selecting multiple and approving at once. | Only single NFA actions are supported. | Pass
UCOTC_169 | Access Restrictions | System does not allow referred user to take any workflow action (approve, reject, forward). | Referred user is not part of workflow | Try to approve/reject/forward | Actions are disabled or not visible. | Pass
UCOTC_171 | Access Restrictions | Comments from referred user become visible to all subsequent reviewers. | Comment is added by referred user. | Login as next reviewer. Open same NFA. | Comment is visible. | Pass
UCOTC_174 | Access Restrictions | Referred user cannot see NFA once it moves to another workflow stage. | NFA is advanced in workflow. | Trigger workflow stage change. Login as referred user. | NFA no longer accessible. | Fail | Visible is All Nfas section
UCOTC_176 | Access Restrictions | Referred NFA should not appear to unauthorized users or outside department. | User from other department tries access. | Try to view NFA via link or referral. | Access denied. | Pass
UCOTC_177 | Access Restrictions | Referred user cannot see approval matrix. | NFA opened by referred user. | Attempt to view approval matrix. | Matrix hidden or access denied. | Fail | Referred User can See
UCOTC_180 | Access Restrictions | Referred NFA should open with annotations and attachments visible. | NFA has annotations/attachments. | Open referred NFA. | Annotations and attachments visible. | Pass
UCOTC_185 | Access Restrictions | Referred user cannot delete or modify uploaded documents. | Attachments exist. | Try to delete/edit files. | Option disabled. | Pass
UCOTC_187 | Access Restrictions | Referred user cannot refer the case again or forward it. | NFA opened. | Attempt to refer or forward. | Action blocked. | Pass
UCOTC_191 | Access Restrictions | Referred user must not see NFAs referred to someone else. | Other user received referral. | Check referred user dashboard. | NFA not visible. | Fail | NFA Referred User is also having initiator access by which it is showing all NFAs
UCOTC_194 | Access Restrictions | Referred user access expires when NFA reaches final approval. | Final approval done. | Try to access NFA. | Access denied. | Pass
UCOTC_196 | Access Restrictions | Referral to same user for same NFA twice should not be allowed. | One referral done. | Try referring again. | Error or warning message. | Fail | Recommener can do multiple time
UCOTC_198 | Access Restrictions | If LDAP account is inactive, referred user should not gain access. | LDAP inactive | Attempt access | Access blocked. | Pass
UCOTC_199 | Access Restrictions | Referred user must not be able to download final dossier. | Final version uploaded. | Try download. | Download option disabled. | Fail | Referred has also he access of other users by which it cannot be checked
UCOTC_200 | Access Restrictions | Attempt to bypass read-only restriction should fail and log a security audit entry. | User tries unauthorized action. | Try editing | Edit fails; audit trail entry created. | Pass
UCOTC_201 | Access Restrictions | Verify that Approver can log in with valid credentials | Approver credentials exist in LDAP | Open login page and enter correct credentials | Approver is logged in and dashboard is shown | Pass
UCOTC_202 | Access Restrictions | Verify that invalid login is not allowed for Approver | Invalid credentials | Enter wrong username or password | Error message shown and login is denied | Pass
UCOTC_205 | Access Restrictions | Verify that all NFA fields are read-only for Approver | NFA opened | Try editing fields like subject, value, etc. | Fields are non-editable (read-only) | Pass
UCOTC_207 | Access Restrictions | Verify that Approver can approve NFA | NFA is valid and ready | Click “Approve”, enter comments, click Submit | NFA is approved and routed accordingly | Pass
UCOTC_211 | Access Restrictions | Verify that only one signature can be set as default | Multiple signatures exist | Try to set two as default | Only one signature is default | Fail | Signature Functionlity is not working as Expekted and not visible in form anywhere
UCOTC_213 | Access Restrictions | Verify that Approver can raise query to Recommender | Recommender exists | Click “Raise Query”, enter comment | NFA sent back to Recommender, comment is recorded | Pass
UCOTC_215 | Access Restrictions | Verify that Approver can reject NFA | NFA has issues | Click Reject, enter comment, confirm | NFA status becomes “Rejected” and sent to END queue | Pass
UCOTC_217 | Access Restrictions | Verify that Approver cannot re-approve rejected NFA | NFA is rejected | Open rejected NFA | Approve button is disabled or hidden | Pass
UCOTC_221 | Access Restrictions | Verify that Approver sees correct NFA title and subject | NFA is visible | Open NFA case | Title and subject match with submission | Pass
UCOTC_222 | Access Restrictions | Verify that Approver can view comments from Recommender | Recommender left comments | Open NFA | Comments section displays recommender notes | Pass
UCOTC_225 | Access Restrictions | Verify that Approver can download final approved document | NFA approved | Open approved NFA | Download button available and works | Pass
UCOTC_231 | Access Restrictions | Verify that Approver cannot access system without login | Not logged in | Try direct NFA URL | Redirected to login page | Pass
UCOTC_235 | Access Restrictions | Verify that Approver cannot edit uploaded files | NFA has uploads | Try to edit/delete files | Not allowed – read-only | Pass
UCOTC_237 | Access Restrictions | Verify that Approver sees version history | Annotated versions exist | Open viewer | Versioning tab is present | Pass
UCOTC_238 | Access Restrictions | Verify that Approver dashboard shows summary of statuses | Approvals, rejections exist | View dashboard tiles | Count of each shown correctly | Pass
UCOTC_242 | Access Restrictions | Verify that Approver cannot approve already closed NFA | NFA closed | Open case | Approve option is disabled | Pass
UCOTC_244 | Access Restrictions | Verify that Approver can see timestamp of each action ¦ NFA history exists ¦ Open audit trail ¦ Shows date and time of all actions ¦ | NFA history exists with recorded actions. | Log in as Approver. Navigate to an NFA with recorded actions. Open the audit trail or history log. | Each action (created, submitted, approved, etc.) is shown with corresponding date and time. | Fail | There is no timestamp n all in the visibility
UCOTC_245 | Access Restrictions | Verify that Approver cannot see draft NFAs ¦ Drafts exist ¦ View dashboard ¦ Drafts are not listed for Approvers ¦ | Draft NFAs exist in the system. | Log in as Approver. View the dashboard or NFA listing. | Draft NFAs are not listed in the Approver’s view. | Fail | Final Approver has the Access of DraftRquest Section
UCOTC_246 | Access Restrictions | Verify that Approver cannot see “Create NFA” button ¦ Logged in as Approver ¦ View dashboard ¦ “Create NFA” is not visible ¦ | User is logged in as Approver. | Navigate to dashboard or home page. | “Create NFA” button is not visible on the interface. | Pass
UCOTC_247 | Access Restrictions | Verify that Approver sees summary sheet questions and answers ¦ Summary added ¦ View NFA ¦ Questions and responses visible ¦ | Summary sheet has been filled out and linked to an NFA. | Open the relevant NFA. Scroll to the summary section. | Approver can view both the questions and the responses. | Pass
UCOTC_248 | Access Restrictions | Verify that Approver cannot delete documents ¦ File attached to NFA ¦ Try to delete ¦ Not allowed ¦ | A document is attached to the NFA. | Open the NFA with the attached file. Attempt to delete the document. | Expected Result: Delete option is disabled or returns an error/denied message. | Pass
UCOTC_250 | Access Restrictions | Verify that Approver cannot raise query if case is already approved | Status: Approved | Try raise query | Not allowed | Pass
UCOTC_252 | Access Restrictions | Verify that Admin can login to the system | Admin credentials are created | Login with valid Admin credentials | Admin is redirected to dashboard | Pass
UCOTC_255 | Access Restrictions | Verify that Admin can view Approved NFA count | At least one NFA is approved | View Admin dashboard | Approved NFA tile displays correct number | Fail | Admin Dashboard don’t show any NFA Numbers
UCOTC_256 | Access Restrictions | Verify that clicking tiles shows detailed report | NFA data exists | Click any tile | Detailed NFA list appears | Pass
UCOTC_257 | Access Restrictions | Verify that Admin can view all NFAs | Admin is logged in | Navigate to report section | Full list of NFAs shown | Pass
UCOTC_264 | Access Restrictions | Verify that Admin can view Master Data Management tab | Admin is logged in | Navigate to MDM tab | MDM screen is visible | Fail | Functionality Not Available
UCOTC_265 | Access Restrictions | Verify that Admin can add new reference data in MDM | MDM tab is open | Click “Add New”, fill values | New data is saved successfully | Fail | Admin don’t have MDM Access
UCOTC_266 | Access Restrictions | Verify that Admin cannot add duplicate entries in MDM | Value already exists | Try to add same value | Error shown for duplicate | Fail | Admin don’t have MDM Access
UCOTC_269 | Access Restrictions | Verify that Admin can delegate NFAs from one user to another | Valid users exist | Select users, set time frame, click delegate | Delegation saved successfully | Fail | “Not Applicable (N/A)” — based on current system design and role permissions.
UCOTC_271 | Access Restrictions | Verify that delegated user cannot re-delegate | Delegation is active | Try to delegate again | System restricts re-delegation | Fail | “Not Applicable (N/A)” — based on current system design and role permissions.
UCOTC_272 | Access Restrictions | Verify that delegation can be deleted | Delegation exists | Click on delete | Delegation is removed | Fail | “Not Applicable (N/A)” — based on current system design and role permissions.
UCOTC_273 | Access Restrictions | Verify that Admin sees audit logs for delegation | Delegation is active | View audit log | Delegation changes are recorded | Fail | “Not Applicable (N/A)” — based on current system design and role permissions.
UCOTC_281 | Access Restrictions | Verify that Admin can see current status of all NFAs | NFA status present | Open report | Status column shows values | Pass
UCOTC_282 | Access Restrictions | Verify that Admin can see “Created By” field | NFA created by users | Open report | Created By column is visible | Pass
UCOTC_283 | Access Restrictions | Verify that Admin can view timestamps | NFA exists | Open report | Shows “Created Date” and “Last Updated” | Pass
UCOTC_285 | Access Restrictions | Verify that Admin sees rejected NFA details | Rejected NFA present | Open report | Reject reason and date shown | Pass
UCOTC_287 | Access Restrictions | Verify that Admin can view final approved dossier | Dossier generated | Open case | Downloadable dossier available | Fail | Not Developed
UCOTC_291 | Access Restrictions | Verify that Admin cannot access dashboard without login | Not logged in | Visit dashboard URL | Redirected to login page | Pass
UCOTC_297 | Access Restrictions | Verify that Admin can log out | Admin is logged in | Click logout | Redirected to login screen | Pass
UCOTC_298 | Access Restrictions | Verify that Admin cannot log in with wrong credentials | Wrong username/password | Try login | Error message shown | Pass
UCOTC_007 | Access Restrictions | Verify that attempting to upload more than 3 documents triggers an error message. | Initiator logged in. | 1. Attempt to upload more than 3 documents. | System throws an error. | Fail | There is no limit for doc upload
UCOTC_035 | Approval Matrix | Verify that the Refer, Forward, and Revoke buttons are hidden when "Is Confidential" is selected. | Initiator logged in. | 1. Select "Is Confidential"; check buttons. | Buttons hidden. | Fail | Confidential Functionalit is not working
UCOTC_036 | Approval Matrix | Verify that only Senior Managers assigned roles have access to NFA creation. | Initiator logged in. | 1. Check access to NFA creation. | Only Senior Managers can create NFA forms. | Pass
UCOTC_042 | Approval Matrix | Verify that supporting documents do not accept files exceeding the assigned 3MB limit. | Initiator logged in. | 1. Attempt to upload file larger than 3MB. | Upload blocked. | Pass
UCOTC_043 | Approval Matrix | Verify that the NFA Number field accepts only numerical values and rejects non-numeric characters. | Initiator logged in. | 1. Enter non-numeric characters in NFA Number field. | Error thrown. | Pass
UCOTC_080 | Approval Matrix | Verify that the recommender cannot refer an NFA without entering a comment. | NFA is ready for referral. | Select a user and click "Refer" without adding comment | Comment is mandatory. System shows error if left blank. | Pass
UCOTC_098 | Audit and Logs | Verify that audit trail entries made by the recommender contain timestamp, action, and user ID. | Recommender performed any action on an NFA. | View audit trail of that NFA. | Log shows username, action taken, and timestamp. | Pass
UCOTC_139 | Audit and Logs | Verify Audit trail logs forwarded user's action with timestamp. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_162 | Audit and Logs | Verify Forwarded user audit trail includes action type, timestamp, and user ID. | User takes action on NFA. | - Go to audit trail of same NFA. | Action is logged with correct metadata. | Pass
UCOTC_175 | Audit and Logs | Referred user sees audit trail, but cannot modify it. | NFA opened by referred user. | View audit trail. Try to edit entries. | View-only access. | Pass
UCOTC_183 | Audit and Logs | System logs referred user activity in audit trail. | User views or comments on NFA. | Perform action. Check audit log. | Activity recorded. | Pass
UCOTC_186 | Audit and Logs | System displays referred user details to recommender for audit. | Referral done. | Login as recommender. Check referral info. | Referred user’s name, comment shown. | Pass
UCOTC_220 | Audit and Logs | Verify that Approver can view audit trail | NFA opened | Click “Audit Trail” tab | All past actions with timestamps are shown | Pass
UCOTC_286 | Audit and Logs | Verify that Admin sees NFA approval trail | NFA processed | Open NFA detail | Action history is shown | Fail | Dashboard at homepag is blnk , user need to click on the any Dashboard option
UCOTC_300 | Audit and Logs | Verify that audit logs are tamper-proof | System log enabled | Try editing logs | Not allowed | Pass
UCOTC_008 | Confidential NFA Handling | Verify that uploading a document larger than 3MB is blocked by the system with a proper error message. | Initiator logged in. | 1. Attempt to upload document larger than 3MB. | System blocks upload. | Pass
UCOTC_032 | Confidential NFA Handling | Verify that filters (Type, Status, Date) on the dashboard display accurate results without missing data. | Initiator logged in. | 1. Apply filters (Type, Status, Date). | Results accurate. | Fail | Some users Dashboard is noteven displaying NFA numbers
UCOTC_033 | Confidential NFA Handling | Verify that the view section correctly lists approved, rejected, and queried NFAs. | Initiator logged in. | 1. Check view section. | Lists correct NFAs. | Pass
UCOTC_071 | Confidential NFA Handling | Verify that Remarks are visible to Initiator in Ongoing Cases and Completed Cases | Initiator has cases in different statuses. | Log in as the Initiator. Navigate to Ongoing and Completed Cases. Check Remarks section. | Remarks are displayed correctly in both sections | Pass
UCOTC_084 | Confidential NFA Handling | Verify that the recommender can revoke a forwarded/referred case only if no action has been taken by the recipient. | Recipient has not responded yet. | Click "Revoke". | Case is revoked successfully with a comment. Email sent. | Pass
UCOTC_090 | Confidential NFA Handling | Verify that NFAs marked as "Is Confidential" are only visible to the recommender if they are part of the approval matrix. | Confidential flag is enabled. | Log in as unrelated user | Confidential NFA is hidden. | Fail | Not Working
UCOTC_103 | Confidential NFA Handling | Verify Confidential NFA Visibility | NFA marked as confidential. | Attempt access from unrelated user. | Access denied. Visible only to involved parties. | Fail | Confidentila Functionality is completely not working
UCOTC_142 | Confidential NFA Handling | Verify Forwarded NFA with 'Is Confidential' flag should not appear to forwarded user. | NFA is forwarded by the recommender. | TBD | TBD | Fail
UCOTC_179 | Confidential NFA Handling | NFA with "Is Confidential" flag should not be referred to other users. | Confidential flag is set. | Try to refer NFA | Referral blocked with warning. | Fail
UCOTC_197 | Confidential NFA Handling | Confidential referrals must be restricted to approvers only. | Confidential. | Attempt to refer to non-approver. | Error shown. | Fail
UCOTC_232 | Confidential NFA Handling | Verify that confidential NFAs are not shown in “All” tab | Confidential NFA exists | View All tab | Confidential NFA is hidden | Fail
UCOTC_233 | Confidential NFA Handling | Verify that confidential NFA appears in “Pending” tab | NFA is confidential and pending | View Pending section | NFA is shown only to Approver | Fail
UCOTC_292 | Confidential NFA Handling | Verify that Admin cannot access confidential NFAs | NFA marked confidential | Login as Admin | NFA not visible | Fail
UCOTC_003 | Create NFA Validations | Verify that the "Create NFA" button is visible only to users with the Initiator role. | Users with different roles logged out. | 1. Log in as Initiator; check for button. 2. Log out and log in as other roles; check for button. | Button visible only to Initiator. | Pass
UCOTC_004 | Create NFA Validations | Verify that the Initiator can start a new NFA and save it as a draft without entering data. | Initiator logged in. | 1. Click "Create NFA". 2. Click "Save as Draft". | NFA saved as draft; listed on dashboard. | Fail
UCOTC_014 | Create NFA Validations | Verify that attempting to submit an NFA with missing mandatory fields prompts validation messages preventing submission. | Initiator logged in. | 1. Attempt to submit NFA with missing fields. | Validation messages displayed. | Pass
UCOTC_017 | Create NFA Validations | Verify that selecting different values in the "Type of NFA" dropdown correctly updates related fields and dependencies. | Initiator logged in. | 1. Select different values in "Type of NFA" dropdown. | All options work as expected. | Pass
UCOTC_018 | Create NFA Validations | Verify that all options in the "Importance" dropdown (Low, Medium, High, Critical) validate correctly when selected. | Initiator logged in. | 1. Select "Importance" dropdown options. | Proper validation for options. | Pass
UCOTC_019 | Create NFA Validations | Verify that the "NFA Value" field becomes mandatory when "Type of NFA" is Procurement. | "Type of NFA" set to Procurement. | 1. Attempt to save NFA. | "NFA Value" field mandatory. | Pass
UCOTC_020 | Create NFA Validations | Verify that the subject field allows a maximum of 255 characters and throws an error if exceeded. | Initiator logged in. | 1. Enter text exceeding 255 characters in subject field. | Error thrown if exceeded. | Pass
UCOTC_021 | Create NFA Validations | Verify that selecting "Is Confidential" instantly clears the existing approval matrix. | Initiator logged in. | 1. Select "Is Confidential"; check matrix. | Matrix cleared instantly. | Fail | All are working same as before
UCOTC_022 | Create NFA Validations | Verify that revoking an NFA is allowed only if it is in the next level’s queue. | NFA in next level’s queue. | 1. Attempt to revoke NFA. | Revoking allowed only in next level’s queue. | Pass
UCOTC_023 | Create NFA Validations | Verify that submitting an NFA without an uploaded signature is blocked by the system. | Initiator logged in. | 1. Attempt to submit NFA without signature. | System blocks submission. | Fail | Signature Functionlity is not working as Expekted and not visible in form anywhere
UCOTC_024 | Create NFA Validations | Verify that enabling the summary sheet by checking the checkbox properly loads related questions. | Initiator logged in. | 1. Check "Add Summary"; verify question loading. | Questions load correctly. | Pass
UCOTC_025 | Create NFA Validations | Verify that the Initiator can upload both "Important" and "Supporting" document types. | Initiator logged in. | 1. Upload "Important" and "Supporting" documents. | Both document types uploaded successfully. | Pass
UCOTC_044 | Create NFA Validations | Verify that every user in the approval flow has a valid relationship with a GM in the system. | Initiator logged in. | 1. Check relation of selected users with GM. | All users related to GM. | Pass
UCOTC_050 | Create NFA Validations | Verify that proper error messages are displayed when invalid file formats are submitted. | Initiator logged in. | Attempt to submit invalid format file. | Proper error message displayed. | Pass
UCOTC_051 | Create NFA Validations | Verify that the user can delete uploaded documents while the case is still in draft mode. | Document uploaded in draft mode. | Delete uploaded document. | Document removed. | Fail | Document Once Create Cannot Be Deleted
UCOTC_095 | Create NFA Validations | Verify that the recommender sees live updates for recently acted NFAs on their dashboard. | Other users act on NFAs in recommender queue. | Open dashboard. Monitor real-time updates after an action is taken elsewhere. | Dashboard updates reflect changes without needing manual refresh. | Pass
UCOTC_113 | Create NFA Validations | Verify Action Constraints Based on NFA Status | Approved NFA. | Try refer, forward, revoke, or document activities. | System restricts all actions post-approval. | Fail | Approved Cases Can Edited
UCOTC_119 | Create NFA Validations | Verify the working of reject NFA | NFA ready for rejection. | Reject with reason. | NFA moved to 'Rejected', becomes read-only. Email sent to all previous users. | Pass | Email is under Development
UCOTC_122 | Create NFA Validations | Verify Forwarded user sees assigned NFA in 'Pending' section only. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_133 | Create NFA Validations | Verify Approving an already revoked NFA should result in an error. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_254 | Create NFA Validations | Verify that Admin dashboard shows In Progress NFA count | At least one NFA is in progress | View Admin dashboard | Tile shows correct count | Fail | Admin User named as prince, have all request on dashboard as 0 but contains all data under that tab
UCOTC_295 | Create NFA Validations | Verify that Admin sees turn-around time of NFA | TAT report loaded | View TAT field | Shows correct time in hours | Pass | Functionality not Added
UCOTC_030 | Dashboard & Filters | Verify that all actions (create, submit, edit, revoke) are logged properly in the audit trail. | Initiator logged in. | 1. Perform actions (create, submit, edit, revoke). | Each action logs an entry in the audit trail. | Pass | Visible is All Nfas section
UCOTC_031 | Dashboard & Filters | Verify that Initiators cannot access or modify NFAs created by other users. | Initiator logged in. | 1. Attempt to access or modify NFA created by another user. | Access or modification not allowed. | Fail | Based on previous failed cases , Initiator is able see the remark of the pedning , closed cases
UCOTC_037 | Dashboard & Filters | Verify that the Initiator can add designated users to the flow, even if matrix data is missing. | Initiator logged in. | 1. Check option to add users. | Option available. | Fail | There is no proper validation for adding users, also LR/LS shows null for manually added User
UCOTC_038 | Dashboard & Filters | Verify that if the designated user is not visible or available, the Initiator cannot submit or save the case as "Draft". | Initiator logged in. | 1. Attempt to submit or save as draft without designated user. | Access denied. | Pass
UCOTC_045 | Dashboard & Filters | Verify that when neither LR nor LS is found, an appropriate error is displayed. | Neither LR nor LS found. | 1. Attempt to submit NFA. | Error displayed. | Fail | There is no proper validation for adding users, also LR/LS shows null for manually added User
UCOTC_053 | Dashboard & Filters | Verify that all form errors are highlighted properly for better visibility. | The Initiator fills out the NFA form but leaves required fields empty | Log in as the Initiator. Start a new NFA. Click "Submit" without entering mandatory details | System highlights all missing fields clearly with visible error indicators | Fail | Fields like Description has no error highlighting and there is no auto - shown to highlighted area
UCOTC_072 | Dashboard & Filters | Verify that the recommender can log in using LDAP credentials and land on their dashboard. | Recommender exists in Active Directory | Navigate to the login page. Enter recommender’s LDAP credentials. Click “Login”. | Recommender is authenticated and redirected to their dashboard. | Pass
UCOTC_073 | Dashboard & Filters | Verify that only NFAs assigned to the recommender are visible on their dashboard. | Recommender has at least one assigned NFA in the approval matrix. | Log in as the recommender. Check the dashboard NFA list. | Only assigned NFAs are visible. | Pass
UCOTC_076 | Dashboard & Filters | Verify that the recommender sees action buttons: Approve, Raise Query, Reject, Refer, Forward, and Revoke when applicable. | NFA is pending and eligible for action. | Open the NFA. Observe available buttons. | All valid actions for the current state are visible and enabled | Pass
UCOTC_085 | Dashboard & Filters | Verify that comments provided by the recommender are stored and visible in the audit trail. | Recommender has acted on an NFA. | View audit trail of that NFA. | Action and comments with timestamp and name are visible. | Fail | Boxes are opened for all who involved in approval
UCOTC_091 | Dashboard & Filters | Verify that dashboard filters like status, date, NFA type work correctly for the recommender. | Multiple NFAs exist. | Use dashboard filters. | Accurate filtered list is displayed. | Pass
UCOTC_092 | Dashboard & Filters | Verify that status changes (e.g., Referred, Approved, Rejected) are updated on the recommender’s dashboard in real time. | NFA undergoes various actions. | Perform actions (refer, approve, reject) on different NFAs. Observe the dashboard immediately after. | Status of NFAs reflects instantly based on latest action taken. | Pass
UCOTC_104 | Dashboard & Filters | Verify Dashboard Filter and Status Accuracy | Multiple NFAs exist. | Use filters and perform actions. | Accurate list displayed. Status updates reflected post each action. | Fail | Dashbaord tabs are showing 0 but under it case are available, andin some usrs , pending nfas are not even working
UCOTC_111 | Dashboard & Filters | Verify Dashboard Realtime Updates | : Ongoing activities with NFAs. | Perform activity and observe dashboard. | Live updates shown. | Fail | Dashboard are not working perfect for all
UCOTC_131 | Dashboard & Filters | Verify Dashboard for forwarded user shows only the count of actionable NFAs. | NFA is forwarded by the recommender. | TBD | TBD | Fail | Not working for all
UCOTC_136 | Dashboard & Filters | Verify Dashboard filters work correctly by NFA Type, Date, and Status. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_167 | Dashboard & Filters | Referred NFA appears in "Referred to Me" section of dashboard. | Referred user is active and logged in. | Login as referred user. Navigate to dashboard. | NFA appears under "Referred to Me" section. | Pass
UCOTC_173 | Dashboard & Filters | If recommender revokes NFA, it disappears from referred user’s dashboard. | NFA already referred. | Login as referred user. | NFA no longer visible. | Pass
UCOTC_189 | Dashboard & Filters | Once action taken by recommender, referred NFA should disappear from referred user dashboard. | Recommender takes action. | Login as referred user. | NFA is no longer listed. | Pass
UCOTC_203 | Dashboard & Filters | Verify that Approver dashboard shows pending NFAs | NFA assigned to Approver | Login and view dashboard | “Pending for Approval” section shows assigned NFA | Pass
UCOTC_204 | Dashboard & Filters | Verify that Approver can open NFA from dashboard | NFA visible in dashboard | Click on NFA row or title | NFA details page is opened | Pass
UCOTC_223 | Dashboard & Filters | Verify that Approver dashboard shows correct count of approved NFAs | Approvals exist | Go to dashboard | Approved count matches actual cases | Fail | show 0 in some cases
UCOTC_224 | Dashboard & Filters | Verify that rejected NFAs are shown in dashboard | NFA rejected | Go to Rejected NFAs tab | NFA appears with status and comments | Fail | show 0 in some cases
UCOTC_243 | Dashboard & Filters | Verify that Approver dashboard loads correctly on slow network | Low internet | Login and navigate | UI still loads with slight delay | Pass
UCOTC_253 | Dashboard & Filters | Verify that Admin dashboard displays total NFA count | Admin is logged in | View Admin dashboard | Tile shows total NFA count | Fail | User lik prince, shows 0 in all requests
UCOTC_270 | Dashboard & Filters | Verify that delegated NFA appears in delegate’s dashboard | Delegation is set | Login as delegate | NFA is visible to delegate | Pass
UCOTC_289 | Dashboard & Filters | Verify that Admin dashboard loads fast | Admin has many NFAs | Login and load dashboard | Loads within 5 seconds | Pass
UCOTC_296 | Dashboard & Filters | Verify that Admin sees pending items on dashboard | Pending NFAs exist | Load dashboard | “In Progress” count shown | Fail | Show 0 for all
UCOTC_039 | Document Uploads | Verify that real-time data updates correctly on the Initiator’s dashboard during case creation. | Initiator logged in. | 1. Check dashboard for real-time data. | Data updated in real-time. | Pass
UCOTC_040 | Document Uploads | Verify that the "Recent NFA’s" section lists data in reverse chronological order (latest to oldest). | Initiator logged in. | 1. Check Recent NFAs. | Data sorted from latest to oldest. | Pass
UCOTC_048 | Document Uploads | Verify that after selecting "Add Summary" in the NFA form, filling the Summary field becomes mandatory. | Initiator logged in. | 1. Select "Add Summary"; attempt to save without filling Summary. | Validation error for Summary field. | Pass
UCOTC_049 | Document Uploads | Verify that entering remarks is mandatory before submitting the NFA. | Initiator logged in. | 1. Fill NFA form attempt to save without Remarks. | Validation error for Remarks field. | Pass
UCOTC_055 | Document Uploads | Verify that users cannot edit documents after they have been submitted. | An NFA has been successfully submitted | Log in as the Initiator. Locate a submitted NFA. Try to edit an attached document | System prevents editing and displays a "Read-Only" notification | Fail | Remarks field is open to edit but not submittable
UCOTC_101 | Document Uploads | Verify signature upload and validation | Signature missing initially. | Upload signature, set default, approve NFA. | Approval fails without signature; default is used during approval. | Fail | Uploading one becomes 2 in the list
UCOTC_102 | Document Uploads | Verify Document Annotation and Versioning | PDF viewer active. | Annotate, save as new version. | All actions logged. Version visible with timestamp and author. | Fail | On no data , it shows a broken error
UCOTC_146 | Document Uploads | Verify Confirm forwarded user cannot delete attached documents. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_147 | Document Uploads | Verify Approve with default signature and verify it reflects in document log. | NFA is forwarded by the recommender. | TBD | TBD | Fail | Nowehere Signature doc shwon
UCOTC_161 | Document Uploads | Verify Forwarded user must upload signature before acting (if not defaulted). | No signature uploaded or defaulted. | - Click approve. | Action blocked with 'Upload Signature' message. | Pass | Signature I not Mandatory
UCOTC_164 | Document Uploads | Verify Forwarded user can print PDF document but not save local copy unless permitted. | Print option available. | - Click print. - Check save option. | Save PDF is blocked; only print allowed. | Pass
UCOTC_181 | Document Uploads | PDF viewer allows referred user to read but not comment or annotate. | PDF exists. | Open PDF. Attempt to annotate. | Annotation tools disabled. | Pass
UCOTC_206 | Document Uploads | Verify that Approver can view attached documents | NFA has upload | Open NFA and scroll to attachment section | All documents listed and downloadable | Pass
UCOTC_209 | Document Uploads | Verify that Approver cannot approve if signature not uploaded | Signature not set | Click Approve | Error shown “Signature not available” | Pass | Signature is not made mandatory
UCOTC_210 | Document Uploads | Verify that Approver can upload signature | Approver profile open | Upload .jpg or .png file under 200KB | Signature saved successfully | Fail | Working but some issues are there
UCOTC_219 | Document Uploads | Verify that documents are pushed to SAP after final approval | Final approval done | Wait for system to process | Files appear in path | Pass
UCOTC_241 | Document Uploads | Verify that Approver sees “Download PDF” button after approval | NFA approved | Open case | Button is active | Pass
UCOTC_251 | Document Uploads | Verify that Approver sees final PDF generated correctly | NFA approved | Open PDF | Content, formatting, and data correct | Fail | Functionality Not Developed
UCOTC_026 | Draft Management | Verify that discarding a draft moves the case to the Discarded queue with the correct status. | Draft NFA exists. | 1. Discard draft NFA. | Case moved to Discarded queue with proper status. | Fail | Draft cannot be discarded
UCOTC_027 | Draft Management | Verify that selecting "Save as Draft" retains all inputs correctly in the database. | Initiator logged in. | 1. Save as Draft; reopen NFA. | All inputs persist in DB. | Fail | No data is Saved
UCOTC_016 | Email Triggers | Verify that an email is triggered to the next recommender, with the Initiator properly included in CC. | NFA submitted. | 1. Check email triggers. | Email sent to next recommender; initiator CC'd. | Fail | Functionality Not Developed
UCOTC_110 | Email Triggers | Verify Email Notifications Post Actions | Reject, Refer, Raise Query, Approve, etc. | Perform action. | Mails triggered to relevant users with correct info. | Fail | Functionlity not Developed
UCOTC_143 | Email Triggers | Verify If email server is down, forwarded NFA still appears in dashboard. | NFA is forwarded by the recommender. | TBD | TBD | Fail | Functionlity not Developed
UCOTC_144 | Email Triggers | Verify Recommender should be notified once forwarded user responds. | NFA is forwarded by the recommender. | TBD | TBD | Fail | Functionlity not Developed
UCOTC_165 | Email Triggers | Verify Forwarded user cannot access NFA from expired link. | NFA link shared is expired or revoked. | - Open shared link. | System shows 'Link expired or invalid'. | Fail | Functionlity not Developed
UCOTC_166 | Email Triggers | Referred user receives email with correct NFA ID and details. | NFA is successfully referred to a valid user. | Refer NFA to a valid user. Check referred user’s email inbox. | Email received with accurate NFA ID, title, and referral comment. | Fail | Functionlity not Developed
UCOTC_188 | Email Triggers | Referral email should include name of recommender and reason/comment. | Email sent. | Open referral email. | Recommender name and comment visible. | Fail | Functionlity not Developed
UCOTC_193 | Email Triggers | Referred users do not get notified of status updates unless shared manually. | Status changes. | Check for notification. | No system notification unless shared manually. | Fail | Functionlity not Developed
UCOTC_212 | Email Triggers | Verify that Approver gets email when NFA is assigned | Email server working | NFA reaches Approver | Email is received with NFA details | Fail | Functionlity not Developed
UCOTC_239 | Email Triggers | Verify that Approver gets email on NFA query raised | Query initiated | System sends alerts | Approver receives email with comment | Fail | Functionlity not Developed
UCOTC_240 | Email Triggers | Verify that Approver is CC’d in approval confirmation | Final approval done | Check inbox | Approver receives confirmation mail | Fail | Functionlity not Developed
UCOTC_288 | Email Triggers | Verify that Admin sees email sent status | Email trigger happened | View mail log | Sent email shown | Fail | Functionlity not Developed
UCOTC_226 | Filter n Sortings | Verify that Approver can filter NFAs by status | Multiple NFAs exist | Apply filter “Pending” or “Rejected” | Results are filtered correctly | Pass
UCOTC_227 | Filter n Sortings | Verify that Approver can filter NFAs by department | NFA data has departments | Use filter “Department” | Results match selected department | Pass
UCOTC_228 | Filter n Sortings | Verify that Approver can search NFA by ID | Know the ID | Enter in search bar | Correct NFA is displayed | Pass
UCOTC_229 | Filter n Sortings | Verify that Approver can search by NFA title | Know the titl | Search by title | Matching NFA appears | Fail | Feature not working on Dashboard of Approver like Devenderkalsi
UCOTC_258 | Filter n Sortings | Verify that Admin can filter NFAs by department | NFA exists for multiple departments | Apply department filter | Only selected department NFAs shown | Fail | Not Working for Admin User like - "prince"
UCOTC_259 | Filter n Sortings | Verify that Admin can filter NFAs by status | Multiple statuses present | Select "Approved" filter | Only approved NFAs appear | Fail | Not Working for Admin User like - "prince"
UCOTC_262 | Filter n Sortings | Verify that Admin can filter user report by department | Users exist in multiple departments | Apply department filter | Filtered user list is shown | Fail | Not Working for Admin User like - "prince"
UCOTC_263 | Filter n Sortings | Verify that Admin can filter user report by name | User exists | Enter name in search | Correct user entry is displayed | Fail | Not Working for Admin User like - "prince"
UCOTC_274 | Filter n Sortings | Verify that Admin can view NFAs by NFA Type filter | Different NFA types exist | Select filter | Filtered result shown | Pass | Working inside all request but on Dashboard main page
UCOTC_277 | Filter n Sortings | Verify that Admin can search NFAs by NFA No | NFA exists | Enter NFA number | Matching NFA is shown | Pass | Working inside all request but on Dashboard main page
UCOTC_278 | Filter n Sortings | Verify that Admin can search NFAs by Title | NFA exists with specific title | Search by title | Results shown | Pass | Working inside all request but on Dashboard main page
UCOTC_279 | Filter n Sortings | Verify that Admin can search NFAs by Subject | Subject is known | Search using subject | Matching NFAs listed | Pass | Working inside all request but on Dashboard main page
UCOTC_280 | Filter n Sortings | Verify that Admin can search by Approver name | Approver exists | Search with name | NFAs approved by that user shown | Pass | Working inside all request but on Dashboard main page
UCOTC_009 | Form Field Validations | Verify that deleting an uploaded document in draft mode removes it from the case without leaving any residual data. | Document uploaded in draft NFA. | 1. Delete uploaded document. | Document removed from case. | Fail | Inititator facing Issue in Uploadig imp. Docsas error is-> 1 error has occurred ORA-01400: cannot insert NULL into ("WKSP_STBPWORKSPACE"."UCO_UPLOAD_SUPPORTING
UCOTC_041 | Form Field Validations | Verify that supporting documents do not accept invalid file formats. | Initiator logged in. | 1. Attempt to upload invalid format file. | Upload blocked. | Fail | Doc. Is not Uploading
UCOTC_046 | Form Field Validations | Verify that the "Save as Draft" option is disabled when no data is entered in the NFA form. | Initiator logged in. | 1. Check Save as Draft option with empty form. | Option disabled. | Fail | It Is available when no data is even entered
UCOTC_047 | Form Field Validations | Verify that dashboard boxes like "All NFA’s," "Pending NFA’s," and "Rejected NFA’s" update dynamically based on user actions. | Initiator logged in. | 1. Perform activities; check dashboard boxes. | Boxes updated. | Fail | Not working for some approvers and admin
UCOTC_096 | Form Field Validations | Verify that when the recommender approves an NFA, it is no longer visible to any referred or forwarded user. | NFA is forwarded or referred and then approved. | Approve the NFA. Log in as the referred/forwarded user. | NFA is no longer visible in their dashboard | Pass
UCOTC_114 | Form Field Validations | Verify Mandatory Comments in All Actions | Action initiated. | Skip comment. | System blocks submission; requires comment. | Pass
UCOTC_117 | Form Field Validations | Verify Approve with and without Comments | NFA ready for approval; signature uploaded. | Attempt to approve with and without comment. | Approval only succeeds with valid comment and signature. Routed to next level. | Pass
UCOTC_126 | Form Field Validations | Verify Forwarded user can reject the NFA with mandatory comments. | NFA is forwarded by the recommender. | TBD | TBD | Fail | No user is visible in Forward User Functionality
UCOTC_128 | Form Field Validations | Verify Attempting to take action without comment prompts validation error. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_156 | Form Field Validations | Verify Forwarded user cannot edit summary sheet fields. | NFA contains summary sheet. | - Open NFA summary sheet. | Fields are read-only. | Fail | No user is visible in Forward User Functionality to Forwading of Case
UCOTC_160 | Form Field Validations | Verify Forwarded user cannot see final approver details. | Forwarded NFA is pending. | - Open approval matrix section. | Approver section is hidden. | Fail | No user is visible in Forward User Functionality to Forwading of Case
UCOTC_170 | Form Field Validations | Referred user can add feedback/comments on referred NFA. | Comment box is enabled. | Enter comment and submit. | Comment is submitted successfully. | Pass
UCOTC_172 | Form Field Validations | Refer action must include mandatory comments to reach referred user. | Attempt referral without comment. | Try to refer NFA without adding a comment. | Error message prompting mandatory comment | Fail | No Remarks been asked for. Auto Generated
UCOTC_178 | Form Field Validations | Attempt to refer NFA to user not registered in system should result in error. | Invalid user selected. | Try referral with unregistered user. | Error message displayed. | Pass
UCOTC_184 | Form Field Validations | System should allow only one response/comment submission per referred user. | Comment submitted. | Attempt to submit second comment. | Error or restriction shown. | Pass
UCOTC_190 | Form Field Validations | Multiple referrals should not create duplicate entries for referred users. | NFA already referred. | Refer again to same user. | No duplicate entry created | Pass
UCOTC_192 | Form Field Validations | Comment box must be enabled and functional. | Referral open. | Access comment box. | Box editable, submit works. | Pass
UCOTC_195 | Form Field Validations | Referred user's comment timestamp should be recorded. | Comment added. | View comment. | Timestamp visible. | Pass
UCOTC_208 | Form Field Validations | Verify that system requires comments on approval | Trying to approve | Click approve without comments | Error shown asking for comment | Pass
UCOTC_214 | Form Field Validations | Verify that Approver must enter comment to raise query | On query popup | Try without comment | Error message is show | Pass
UCOTC_216 | Form Field Validations | Verify that Approver must enter comment when rejecting | NFA open | Try to reject without comment | Validation message shown | Pass
UCOTC_218 | Form Field Validations | Verify that final Approver's action triggers dossier generation | Approver is last in matrix | Approve NFA | Dossier PDF generated and saved in system | Fail | Functionality Under Development
UCOTC_234 | Form Field Validations | Verify that Approver cannot forward NFA | Approvers don’t forward | Open NFA | No “Forward” option for Approver | Pass
UCOTC_236 | Form Field Validations | Verify that Approver can view annotations from Recommenders | Recommender added notes | Open document viewer | Annotations are visible | Pass
UCOTC_249 | Form Field Validations | Verify that Approver sees NFA value with and without GST ¦ NFA has both values ¦ Open case ¦ Fields show correct numbers ¦ | NFA includes both GST-inclusive and exclusive values. | Open the NFA record. | Both values (with and without GST) are clearly shown in the relevant fields. | Pass
UCOTC_105 | Forward/Refer | Verify Validation on Invalid Referrals or Missing Comments | Try refer without comment or to unregistered user. | Perform action. | System blocks and shows appropriate error message. | Pass
UCOTC_106 | Forward/Refer | Verify Tooltip/Help Text on Action Buttons | NFA open. | Hover on buttons. | Tooltip/help text displayed. | Pass
UCOTC_108 | Forward/Refer | Verify Audit Trail and Document Visibility | Actions or document versions exist. | Open trail/version section. | All actions and versions displayed with metadata. | Pass
UCOTC_120 | Forward/Refer | Verify the Refer/Forward NFA to assigned users | Valid users onboarded. | Refer/forward NFA to users. | Email triggered. NFA visible on their dashboards. Recommender can act post-feedback. | Pass
UCOTC_121 | Forward/Refer | Verify forwarded user receives email notification with correct NFA ID and comments. | NFA is forwarded by the recommender. | TBD | TBD | Pass | Functionality Under Development
UCOTC_123 | Forward/Refer | Verify Forwarded user cannot view NFAs not assigned to them. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_127 | Forward/Refer | Verify Forwarded user action does not change final routing but assists the recommender. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_129 | Forward/Refer | Verify Revoke by the recommender before forwarded user takes action removes it from dashboard. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_132 | Forward/Refer | Verify Forwarded user cannot perform refer/forward/revoke actions. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_134 | Forward/Refer | Verify Forwarded user can view previous comments/annotations in the PDF viewer. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_135 | Forward/Refer | Verify Forwarded user has no access to approval matrix view. | NFA is forwarded by the recommender. | TBD | TBD | Fail
UCOTC_137 | Forward/Refer | Verify Forwarded user cannot modify any data fields. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_140 | Forward/Refer | Verify Forwarded user cannot take action if the case is revoked after forwarding. | NFA is forwarded by the recommender. | TBD | TBD | Fail | Functionality of Forward is not working as of now
UCOTC_145 | Forward/Refer | Verify Forwarded user's approval status shown in audit history. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_148 | Forward/Refer | Verify Rejected NFA by forwarded user still needs recommender’s final decision. | NFA is forwarded by the recommender. | TBD | TBD | Pass
UCOTC_154 | Forward/Refer | Verify Forwarded user cannot revoke another forwarded user’s actions. | Multiple forwards are issued. | - Login as forwarded user A. - Attempt to revoke B’s action. | Access denied for revoking other's actions. | Pass
UCOTC_155 | Forward/Refer | Verify Forwarded user sees tooltip guidance for each available action. | NFA is pending for forwarded user. | - Hover over action buttons. | Tooltip text appears with descriptions. | Fail | Functionality of Forward is not working as of now
UCOTC_168 | Forward/Refer | Referred user can open and view NFA details in read-only mode. | Referral has been received. | Open referred NFA. | NFA is viewable but fields are non-editable. | Pass
UCOTC_182 | Forward/Refer | Test accessibility features (screen reader, tab navigation) on referred user dashboard. | Dashboard opened. | Use screen reader. Navigate usng keyboard. | All elements accessible. | Pass
UCOTC_001 | Login | Verify that the Initiator can log in using valid credentials and is redirected to their dashboard without errors. | LDAP server is on, valid Initiator user account exists. | 1. Open login page. 2. Enter valid Initiator credentials. 3. Click "Login". | User is authenticated; redirected to dashboard. | Pass
UCOTC_002 | Login | Verify that invalid LDAP credentials display proper error messages and prevent unauthorized access. | Access to the login page. | 1. Open login page. 2. Enter invalid credentials. 3. Click "Login". | Error message displayed; access denied. | Pass
UCOTC_012 | Lower Case Management | Verify that the system displays a warning if neither LR nor LS users are found in the matrix. | Neither LR nor LS found in matrix. | 1. Attempt to submit NFA. | System shows warning. | Fail | Showing NULL in Approval Matric and no error
UCOTC_013 | Lower Case Management | Verify that the system correctly accepts the matrix when only LS is found and ignores LR. | Only LS found in matrix. | 1. Attempt to submit NFA. | Matrix accepted; LR ignored. | Pass
UCOTC_099 | Lower Case Management | Verify that the recommender’s LR and LS alignment is correctly shown in the approval matrix. | Approval matrix is auto-fetched from HRMS. | Open the matrix view of an NFA. | LR appears in lower position, LS in upper. Recommender is correctly placed. | Pass
UCOTC_112 | Lower Case Management | Verify LR/LS Alignment Validation | : HRMS sync active. | View approval matrix. | LR and LS correctly assigned. | Pass
UCOTC_006 | NFA Document Upload | Verify that uploading a document under 3MB successfully attaches it to the NFA without issues. | Initiator logged in. | 1. Upload document under 3MB. | Document attached properly. | Fail | Doc. Is not Uploading as of now
UCOTC_010 | NFA Form Page | Verify that the approval matrix is auto-populated based on HRMS data when an NFA is created. | Initiator logged in. | 1. Create NFA; check approval matrix. | Matrix auto-populated based on HRMS data. | Pass
UCOTC_011 | NFA Form Page | Verify that if the approval matrix fails to populate, the Initiator can manually add approvers. | Approval matrix not auto-populated. | 1. Manually add approvers. | Approvers added successfully. | Pass
UCOTC_005 | Recommender Functionalities | Verify that drafts can be reopened, edited, and updated without losing previously entered data. | Draft NFA exists. | 1. Open draft NFA. 2. Make edits. 3. Save changes. | Edits saved without data loss. | Fail | Entered empty forms as well
UCOTC_056 | Recommender Functionalities | Verify that remarks are required when resubmitting an NFA after a query is raised. | A recommender has raised a query on the NFA | Log in as the Initiator. Open the NFA with a query. Attempt to resubmit without entering remarks | System prevents submission and shows an error stating remarks are mandatory | Pass
UCOTC_058 | Recommender Functionalities | Verify that errors are displayed if no approvers are selected when submitting the NFA. | Initiator has not added approvers in the approval matrix | Log in as the Initiator. Start a new NFA and leave approval matrix empty. Click "Submit. | System prevents submission and displays an error requiring at least one approver | Pass
UCOTC_059 | Recommender Functionalities | Verify that confidential NFAs are visible only to the Initiator and authorized users. | The Initiator marks an NFA as "Confidential" | Log in as the Initiator. Create an NFA and select "Is Confidential." Check visibility of the NFA for other users | NFA does not appear in "All Cases" and is visible only to assigned users | Fail | Form is created even when LR/LS is NULL for selected approvers in matrix
UCOTC_063 | Recommender Functionalities | Verify that scrolling through the NFA form automatically highlights any errors present. | Initiator is working on an incomplete NFA form | Log in as the Initiator. Start an NFA form and leave required field blank. Click "Submit." Scroll through the form | System highlights errors as the user scrolls, improving visibility | Pass
UCOTC_068 | Recommender Functionalities | Verify that the NFA creation date updates dynamically upon new form entry. | Initiator starts a new NFA | Log in as the Initiator. Create a new NFA. Check the creation date field | Date auto-fills with the current system date and time | Pass
UCOTC_069 | Recommender Functionalities | Verify that the Initiator can remove previously added approvers if needed. | Initiator has manually added approvers | Log in as the Initiator Open approval matrix Remove an approver | System successfully removes the selected approver before submission | Pass
UCOTC_070 | Recommender Functionalities | Verify that the Initiator cannot click "Confirm" without selecting data in the required fields. | Initiator is filling an NFA form | Log in as the Initiator. Leave requird fields empty Click "Confirm" | System should block confirmation and highlight missing fields | Pass
UCOTC_082 | Recommender Functionalities | Verify that the recommender can forward an NFA to multiple users and each gets an email notification. | NFA is ready to forward. | Select multiple users. Click "Forward" with a comment. | NFA is visible to each forwarded user. Each receives email. | Fail | Forward n Email not working
UCOTC_083 | Recommender Functionalities | Verify that the recommender cannot revoke an NFA if the next user has already taken action. | Next user has already acted. | Try clicking "Revoke" | Revoke is not available | Pass
UCOTC_086 | Recommender Functionalities | Verify that the recommender cannot create, discard, or modify NFAs. | Logged in as recommender. | Try accessing "Create NFA", "Discard", or edit functions. | Access denied or controls not visible. | Pass
UCOTC_087 | Recommender Functionalities | Verify that the recommender can annotate documents using highlight, text, drawing, and table tools. | NFA has attached PDF documents. | Open the document viewer. Use annotation tools. | Annotations are applied. | Pass
UCOTC_109 | Reports n Exports | Verify Report Access and Downloads | : Report access granted. | Download reports. | Excel report generated. | Fail | Functionality Under Development
UCOTC_260 | Reports n Exports | Verify that Admin can export NFA report to Excel | NFA report available | Click on Export button | Excel file is downloaded | Fail | Functionality Under Development
UCOTC_261 | Reports n Exports | Verify that Admin can view detailed user report | Admin is logged in | Go to User Report | User details are listed | Fail | Functionality Under Development
UCOTC_275 | Reports n Exports | Verify that Admin can view NFAs by value range | Multiple NFA values exist | Set range filter | NFAs within range are displayed | Pass
UCOTC_276 | Reports n Exports | Verify that pagination works in report view | Many NFAs exist | Scroll down | Next page loads | Fail
UCOTC_284 | Reports n Exports | Verify that Admin can filter by NFA importance | NFAs have importance tags | Filter by “Critical” | Only critical NFAs shown | Pass
UCOTC_293 | Reports n Exports | Verify that Admin can view NFA by date range filter | NFAs have dates | Set date filter | NFAs in date range shown | Pass
UCOTC_294 | Reports n Exports | Verify that Admin can view TAT report | TAT report available | Click TAT tab | TAT report is displayed | Fail
UCOTC_301 | Reports n Exports | Verify that Admin can view NFAs by amount filter | Multiple NFA amounts exist | Filter by amount | Correct list shown | Pass
UCOTC_302 | Reports n Exports | Verify that Admin can download multiple reports | Reports exist | Click download | All reports saved as Excel | Fail
UCOTC_054 | Session Activity | Verify that session timeout logs out the Initiator after a predefined period of inactivity. | Initiator is logged into the system. System has a predefined session timeout | Log in as the Initiator. Remain inactive beyond the timeout duration. Try to perform any action after timeout | System auto-logs out the user and redirects to the login page | Pass
UCOTC_066 | Session Activity | Verify that filtered reports can be downloaded correctly. | Initiator applies filters to reports | Log in as the Initiator. Filter reports by date/status. Click "Download" | Filtered report is downloaded without errors | Fail
UCOTC_088 | Session Activity | Verify that each document annotation by the recommender is versioned and tracked. | At least one annotation saved. | Save the annotation. View version history. | Version history includes annotations with timestamp. | Pass
UCOTC_230 | Session Activity | Verify that Approver is logged out on session timeout | Session idle | Wait 30 mins | Auto logout occurs | Pass
UCOTC_290 | Session Activity | Verify that Admin is redirected to login on session expiry | Idle session | Wait 30 minutes | Redirected to login screen | Pass
UCOTC_299 | Session Activity | Verify that Admin is notified of expired delegation | Delegation expired | View delegation list | Marked as expired | Pass
UCOTC_267 | System Updates | Verify that Admin can edit MDM values | MDM entry exists | Click edit, modify value | Updated value is saved | Fail
UCOTC_268 | System Updates | Verify that system stores last updated info in MDM | Admin updates value | View audit log | Shows “last updated by” and date | Pass
UCOTC_015 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that submitting a fully completed NFA moves it to the next user in the matrix without issues. | Fully-filled NFA. | 1. Submit NFA. | NFA moves to next user in matrix. | Pass
UCOTC_028 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that after a query is raised, adding mandatory comments is enforced before resubmitting the NFA. | Query raised on NFA. | 1. Attempt to resubmit NFA. | Comments mandatory before resubmission. | Pass
UCOTC_052 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that the Initiator sees a confirmation dialog before discarding an NFA. | The Initiator has an active draft or pending NFA | Log in as the Initiator. Open the draft or pending NFA. Click "Discard" | A confirmation dialog appears, asking for user confirmation before discarding | Pass
UCOTC_060 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that an NFA cannot be revoked if it has already progressed too far in the approval process. | NFA has passed initial approval stages | Log in as the Initiator. Locate an NFA beyond the first-level approval. Try to revoke it | System prevents revocation and shows a message that the NFA is too far in the process | Fail | Shows warning but not saves entered an data
UCOTC_061 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that users cannot switch to other sidebar functionalities while working on an NFA. | Initiator is actively filling out an NFA form | Log in as the Initiator. Start a new NFA entry. Try clicking on another sidebar feature before saving | System blocks switching and prompts user to save or discard the NFA first | Pass
UCOTC_062 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that the user can log out while in the NFA form page without encountering errors. | Initiator has an unsaved NFA open | Log in as the Initiator. Open an NFA creation page. Click "Logout" | System successfully logs out the user and saves any existing progress as a draft | Pass
UCOTC_064 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that reports shown in the system can be exported easily. | Initiator has access to reports section | Log in as the Initiator. Navigate to reports. Click "Export" | Report is successfully downloaded in Excel/PDF format | Fail
UCOTC_065 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that users can apply filters while viewing reports. | Reports exist in the dashboard | Log in as the Initiator. Navigate to reports. Apply filters (Type, Date, Status) | Reports update correctly based on applied filters | Fail
UCOTC_077 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that the recommender cannot approve an NFA without entering a comment. | NFA is ready for approval. | Open NFA. Click "Approve" without filling comment. | System shows validation error and blocks approval. | Pass
UCOTC_081 | Workflow Actions (Submit, Revoke, Query, Reject) | Verify that the recommender receives an email notification after being assigned an NFA. | An NFA is submitted with the recommender in its matrix. | Submit NFA as initiator. Check recommender’s email inbox. | Email is triggered with NFA details. | Fail

## Pivot
Count of Status | Status
Modules | Fail | Pass | Grand Total
Access Restrictions | 29 | 58 | 87
Approval Matrix | 1 | 4 | 5
Audit and Logs | 1 | 8 | 9
Confidential NFA Handling | 9 | 4 | 13
Create NFA Validations | 6 | 16 | 22
Dashboard & Filters | 12 | 16 | 28
Document Uploads | 6 | 12 | 18
Draft Management | 2 |  | 2
Email Triggers | 12 |  | 12
Filter n Sortings | 5 | 8 | 13
Form Field Validations | 9 | 16 | 25
Forward/Refer | 3 | 16 | 19
Login |  | 2 | 2
Lower Case Management | 1 | 3 | 4
NFA Document Upload | 1 |  | 1
NFA Form Page |  | 2 | 2
Recommender Functionalities | 3 | 9 | 12
Reports n Exports | 6 | 4 | 10
Session Activity | 1 | 5 | 6
System Updates | 1 | 1 | 2
Workflow Actions (Submit, Revoke, Query, Reject) | 4 | 6 | 10
Grand Total | 112 | 190 | 302

## Module Details
Module Name | Total Cases Identified | Total Cases Tested | Total Cases Passed | Total Cases Failed
Access Restrictions | 203 | 116 | 87 | 29
Approval Matrix | 11 | 6 | 5 | 1
Audit and Logs | 19 | 10 | 9 | 1
Confidential NFA Handling | 35 | 22 | 13 | 9
Create NFA Validations | 50 | 28 | 22 | 6
Dashboard & Filters | 68 | 40 | 28 | 12
Document Uploads | 42 | 24 | 18 | 6
Draft Management | 6 | 4 | 2 | 2
Email Triggers | 36 | 24 | 12 | 12
Filter n Sortings | 31 | 18 | 13 | 5
Form Field Validations | 59 | 34 | 25 | 9
Forward/Refer | 41 | 22 | 19 | 3
Login | 4 | 2 | 2 | 0
Lower Case Management | 9 | 5 | 4 | 1
NFA Document Upload | 3 | 2 | 1 | 1
NFA Form Page | 4 | 2 | 2 | 0
Recommender Functionalities | 27 | 15 | 12 | 3
Reports n Exports | 26 | 16 | 10 | 6
Session Activity | 13 | 7 | 6 | 1
System Updates | 5 | 3 | 2 | 1
Workflow Actions (Submit, Revoke, Query, Reject) | 24 | 14 | 10 | 4
Grand Total | 302 | 302 | 190 | 112